## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | Create TA Profile | As a TA I want to create an applicant profile So that I can provide my personal and academic information for TA recruitment applications. | High | 1 | This is an example. This is a new line 1. List 1 2. List 2 3. List 3 |  |  | 2026-03-15 | 2026-04-04
2 | Upload CV | As a TA I want to upload my CV So that the school and MOs can review my professional experience and qualifications for TA roles. | Relatively High | 2 |  |  |  | 2026-04-05 | 2026-04-19
3 | Browse Job Listings | As a TA I want to find available jobs So that I can browse and select the TA positions that match my skills and availability. | High | 1 |  |  |  | 2026-03-15 | 2026-04-04
4 | Apply for Position | As a TA I want to apply for jobs So that I can submit my candidacy for the TA positions I am interested in. | High | 1 |  |  |  | 2026-03-15 | 2026-04-04
5 | Track Application Status | As a TA I want to check my application status So that I can stay informed about whether my application is under review, accepted or rejected. | Relatively High | 2 |  |  |  | 2026-04-05 | 2026-04-19
6 | Post Job Vacancy | As a MO I want to post jobs So that I can publish TA vacancy information for the academic modules I am responsible for. | High | 1 |  |  |  | 2026-03-15 | 2026-04-04
7 | Select TA Candidate | As a MO I want to select applicants for jobs So that I can choose the most suitable TA candidates for my module's vacant positions. | Relatively High | 2 |  |  |  | 2026-04-05 | 2026-04-19
8 | Monitor TA Workload | As an Admin I want to check a TA’s overall workload So that I can ensure TAs are not overloaded and allocate work reasonably across the school. | Medium | 3 |  |  |  | 2026-04-20 | 2026-05-02
9 | Skill-Based Job Matching | As a MO I want the system to match skills between jobs and applicants So that relevant TA candidates can be quickly identified for vacant positions. | Medium | 3 |  |  |  | 2026-04-10 | 2026-05-02
10 | Identify Skill Gaps | As a TA I want the system to identify my missing skills for applied jobs So that I can understand the skill gaps and improve myself to be more competitive for future TA applications. | Medium | 3 |  |  |  | 2026-04-20 | 2026-05-02
11 | Auto-Balance Workload | As an Admin I want the system to balance TA workload automatically So that I can distribute TA tasks fairly and optimise the utilisation of TA resources across the school. | Medium | 3 |  |  |  | 2026-04-20 | 2026-05-02
12 | View Applicant Competition | As a TA I want to view the real-time number of applicants for each position So that I can assess the competition level of each TA role and make more informed application decisions. | Low | 4 |  |  |  | 2026-05-03 | 2026-05-17
13 | Filter by Employment Type | As a TA I want the system to distinguish between part-time and full-time TA positions So that I can filter and apply for the positions that align with my available working time and commitment level. | Low | 4 |  |  |  | 2026-05-03 | 2026-05-17
14 | AI-Powered Job Recommendations | As a TA I want the system to generate AI-powered intelligent job recommendations based on my personal demands So that I can quickly find the most matching TA positions that fit my skills, availability and career needs | Low | 4 |  |  |  | 2026-05-03 | 2026-05-17